WWRGD Worldwide Responsible General Development

GENERAL CONTRACTOR RISK SCORING MATRIX Quantitative Risk Evaluation Framework for General Contractor Vendors

| Document ID | Version | Effective Date | Classification |
| --- | --- | --- | --- |
| WWRGD-RSM-GC-001 | v2.0 | January 1, 2025 | CONFIDENTIAL |

SCOPE & PURPOSE This matrix provides a standardized, quantitative framework for evaluating General Contractor (GC) vendor risk. It applies to all GC vendors bidding on or engaged in construction, renovation, infrastructure, or capital improvement projects for WWRGD. The 400-point scoring system, six weighted risk categories, and four-tier risk classification enable consistent, defensible, and comparable GC vendor assessments across the WWRGD project portfolio. This document is the companion scoring guide to the WWRGD Enhanced GC RFI (WWRGD_Enhanced_GC_RFI.xlsx).

| APPLIES TO All General Contractor vendors — construction, renovation, infrastructure, and capital improvement projects | COMPANION DOCUMENT WWRGD Enhanced GC RFI ¦ WWRGD_Enhanced_GC_RFI.xlsx |
| --- | --- |

SECTION A Critical Risk Indicators (Automatic Disqualification)

The following indicators represent conditions that require immediate escalation and may result in automatic disqualification from General Contractor consideration, regardless of composite scoring. Any single failure should trigger review by the appropriate approval authority.

|  | Critical Risk Indicator | Threshold / Disqualifying Condition | Status Check |
| --- | --- | --- | --- |
|  | Active Litigation | Pending or active litigation exceeding $5,000,000 | ☐ Pass / ☐ Fail |
|  | OSHA Violations | Willful or Repeat citations within the past 3 years | ☐ Pass / ☐ Fail |
|  | Financial Distress | Negative cash flow, covenant violations, bankruptcy filing, or formal insolvency | ☐ Pass / ☐ Fail |
|  | Debarment Status | Any active federal, state, or local debarment or exclusion from public contracts | ☐ Pass / ☐ Fail |
|  | Safety Metrics | EMR > 1.2 or TRIR > 3.0 (3-year rolling average) | ☐ Pass / ☐ Fail |
|  | Bond Capacity | Bonding capacity insufficient for project size or scope requirements | ☐ Pass / ☐ Fail |
|  | License Status | Expired, suspended, or revoked contractor licenses required for project work | ☐ Pass / ☐ Fail |

NOTE: A "Fail" on any indicator above requires immediate escalation to VP/Executive level before proceeding with scoring. Critical Risk Indicators are evaluated independently of the composite scoring in Sections B–F.

SECTION B Weighted Risk Categories

Each of the six risk categories below is assigned a weight reflecting its relative importance to overall General Contractor risk. Scores are assigned on a 1–4 scale for each category (see Section C for detailed rubrics). The maximum composite score is 400 points.

| Risk Category | Weight | Max Score | Rationale |
| --- | --- | --- | --- |
| Financial Stability | 30% | 120 pts | Highest impact on project completion ability and long-term contractor viability |
| Safety Performance | 20% | 80 pts | Critical to WWRGD liability exposure, workforce protection, and project site safety obligations |
| Quality / Performance History | 20% | 80 pts | Direct indicator of the contractor's ability to deliver to agreed specifications, timelines, and quality standards |
| Operational Capacity | 20% | 80 pts | Ensures the contractor has sufficient bandwidth, workforce, and equipment to execute the project alongside existing commitments |
| Compliance Record | 10% | 20 pts | Regulatory, legal, and contractual compliance risk mitigation across all applicable jurisdictions and industry standards |
| Technology Capabilities | 10% | 20 pts | Efficiency, modern project management platforms, BIM/VR capabilities, and cybersecurity posture |
| TOTAL | 100% | 400 pts | Maximum Composite Score |

SECTION C Detailed Scoring Rubrics (1–4 Scale)

For each category, assign a score of 1 (Poor), 2 (Fair), 3 (Good), or 4 (Excellent) based on the criteria below. Use the highest fully-met score level; partial credit within a band is not applicable.

| C1. Financial Stability 30% weight |  |  |
| --- | --- | --- |
| Score | Level | Criteria |
| 4 | Excellent | D/E ratio < 0.5; EMR < 0.85; bond capacity >150% of project value; audited financials with clean opinion for 3+ consecutive years |
| 3 | Good | D/E ratio 0.5–1.0; EMR 0.85–1.0; adequate bonding with modest margin; audited or reviewed financials with minor audit findings |
| 2 | Fair | D/E ratio 1.0–2.0; EMR 1.0–1.2; limited bonding capacity relative to project value; some financial concerns or qualified audit opinions |
| 1 | Poor | D/E ratio > 2.0; EMR > 1.2; bonding issues or inability to bond; significant financial stress, negative equity, or adverse audit findings |

| C2. Safety Performance 20% weight |  |  |
| --- | --- | --- |
| Score | Level | Criteria |
| 4 | Excellent | TRIR < 1.0; zero serious OSHA violations in the past 3 years; comprehensive written safety program with proactive safety culture and dedicated safety officer |
| 3 | Good | TRIR 1.0–2.0; minor violations only (no willful/repeat); documented safety program with regular employee training and incident review processes |
| 2 | Fair | TRIR 2.0–3.0; some serious violations with documented remediation; basic safety compliance meeting minimum OSHA requirements |
| 1 | Poor | TRIR > 3.0; willful or repeat OSHA violations; inadequate or non-existent safety program; pattern of workplace incidents |

| C3. Quality / Performance History 20% weight |  |  |
| --- | --- | --- |
| Score | Level | Criteria |
| 4 | Excellent | Cost Performance Index (CPI) > 0.95; Schedule Performance Index (SPI) > 0.95; defect rate < 5%; 90%+ client retention rate on completed projects |
| 3 | Good | CPI 0.90–0.95; SPI 0.90–0.95; defect rate 5–10%; client retention rate 75–90%; minor punch-list items resolved promptly |
| 2 | Fair | CPI 0.85–0.90; SPI 0.85–0.90; defect rate 10–15%; client retention rate 60–75%; recurring quality issues with documented remediation |
| 1 | Poor | CPI < 0.85; SPI < 0.85; defect rate > 15%; client retention < 60%; history of project failures, claims, or terminated contracts |

| C4. Operational Capacity 20% weight |  |  |
| --- | --- | --- |
| Score | Level | Criteria |
| 4 | Excellent | Current capacity utilization < 70%; deep bench strength in key trades and project management; proven scalability with documented ability to staff up rapidly |
| 3 | Good | Capacity utilization 70–85%; adequate staffing for project requirements; some scalability with subcontractor relationships or temp workforce options |
| 2 | Fair | Capacity utilization 85–95%; limited bench strength; capacity concerns may affect project start dates or milestone delivery |
| 1 | Poor | Capacity utilization > 95%; no meaningful bench strength; contractor is overextended across multiple projects; high risk of workforce or equipment shortfalls |

| C5. Compliance Record 5% weight |  |  |
| --- | --- | --- |
| Score | Level | Criteria |
| 4 | Excellent | Zero regulatory violations in the past 5 years; proactive compliance management program; third-party compliance audits completed; no open enforcement actions |
| 3 | Good | Minor violations only (fully remediated); documented compliance program; active license and insurance maintenance; no pattern of non-compliance |
| 2 | Fair | Some violations with documented remediation plans; basic compliance meeting minimum regulatory requirements; some lapses in insurance or licensing maintenance |
| 1 | Poor | Significant violations or pattern of non-compliance; inadequate compliance program; open enforcement actions; lapses in required licenses or insurance |

| C6. Technology Capabilities 5% weight |  |  |
| --- | --- | --- |
| Score | Level | Criteria |
| 4 | Excellent | BIM/VR capabilities; Procore proficiency (or equivalent tier-1 PM platform); SOC 2 certified or equivalent cybersecurity posture; advanced real-time reporting and dashboard capabilities |
| 3 | Good | Standard project management software in use; basic cybersecurity controls; adequate reporting and document management; capable of integrating with WWRGD systems |
| 2 | Fair | Limited technology adoption; basic or fragmented PM tools; minimal security measures; reporting requires significant manual effort |
| 1 | Poor | Primarily paper-based processes; no meaningful cybersecurity program; unable to provide electronic reporting, RFI tracking, or document control |

SECTION D Risk Level Definitions

The composite score maps to one of four risk tiers. These thresholds drive approval authority, required actions, and contract enhancements (see Section F). Risk levels are consistent across the WWRGD vendor evaluation framework to enable cross-portfolio comparability.

| Composite Score Range | Risk Level | Color Code | Decision Framework |
| --- | --- | --- | --- |
| 320–400 pts (80–100%) | LOW RISK | ⬤ GREEN | APPROVE — Category Manager authorization; standard MSA terms; routine monitoring |
| 240–319 pts (60–79%) | MEDIUM RISK | ⬤ YELLOW | CONDITIONAL APPROVAL — Director level authorization; enhanced monitoring required; quarterly reviews |
| 160–239 pts (40–59%) | HIGH RISK | ⬤ ORANGE | EXECUTIVE REVIEW REQUIRED — VP/Executive authorization; weekly reporting; dedicated oversight assigned |
| < 160 pts (< 40%) | CRITICAL RISK | ⬤ RED | NOT RECOMMENDED — Disqualify; formal rejection letter issued; 12-month waiting period for re-application |

SECTION E Calculation Methodology

Follow this five-step process to calculate a composite risk score for each General Contractor vendor under evaluation:

| Step | Description |
| --- | --- |
| Step 1: Screen for Critical Risk Indicators | Review all seven indicators in Section A. Any single "Fail" result triggers automatic escalation to VP/Executive level. Do not proceed with composite scoring until Section A review is complete and documented. |
| Step 2: Score Each Category (1–4 Scale) | Using the rubrics in Section C, assign a score of 1 (Poor), 2 (Fair), 3 (Good), or 4 (Excellent) for each of the six risk categories. Document your evidence basis for each score in the vendor file. |
| Step 3: Apply Category Weights | Multiply each category score by its assigned weight percentage to calculate the weighted score for that category. Weights are defined in Section B. |
| Step 4: Calculate the Composite Score (Max 400) | Sum all six weighted scores to arrive at the composite score. The maximum achievable score is 400 points (all categories rated Excellent × 100%). |
| Step 5: Map to Risk Level | Using the threshold table in Section D, identify which risk tier the composite score falls into. Apply the corresponding decision framework from Section F. |

WORKED EXAMPLE — General Contractor Evaluation

Scenario: WWRGD is evaluating a mid-market General Contractor for a $12M commercial renovation project. Following full RFI review, site visit, and reference checks, the following scores were assigned: Section A Result: All 7 Critical Risk Indicators passed — scoring proceeds.

| Risk Category | Score (1–4) | Weight | Weighted Score | Score Basis |
| --- | --- | --- | --- | --- |
| Financial Stability | 3 | 30% | 75 pts | D/E ratio 0.8; EMR 0.92; adequate bonding; reviewed financials |
| Safety Performance | 4 | 20% | 80 pts | TRIR 0.7; zero serious violations 3 yrs; dedicated safety officer |
| Quality / Performance History | 3 | 20% | 80 pts | CPI 0.93; SPI 0.91; 7% defect rate; 82% client retention |
| Operational Capacity | 3 | 20% | 45 pts | 78% utilization; adequate crew; some scalability demonstrated |
| Compliance Record | 4 | 10% | 20 pts | Zero violations 5 yrs; proactive compliance program; annual audits |
| Technology Capabilities | 2 | 10% | 20 pts | Basic PM software; limited BIM; minimal cybersecurity controls |
| COMPOSITE TOTAL |  | 100% | 320 pts | LOW RISK — Green Tier |

✔ RESULT: The contractor scores 320 out of 400 points (80%), placing it in the LOW RISK (Green) tier. Category Manager may approve under standard MSA terms. Recommended monitoring: quarterly progress reviews, SLA compliance tracking, and annual re-scoring at contract renewal.

SECTION F Decision-Making Framework

The following framework maps composite scores to approval authorities, required actions, and contract enhancements. All decisions must be documented in the vendor file and linked to this scoring matrix.

| Risk Level | Approval Authority | Required Actions | Contract Enhancements | Re-Application |
| --- | --- | --- | --- | --- |
| LOW RISK 320–400 pts | Category Manager | • Standard due diligence review • Annual re-scoring at renewal • Quarterly business reviews | • Standard MSA terms • Standard retainage rates | N/A — Not Required |
| MEDIUM RISK 240–319 pts | Director Level | • Enhanced monitoring program • Quarterly reviews required • Semi-annual re-scoring | • Performance bonds required • Parent guarantees where applicable • Enhanced insurance requirements | Eligible after 6 months with documented improvements |
| HIGH RISK 160–239 pts | VP / Executive | • Weekly progress reporting • Dedicated WWRGD oversight officer • Monthly executive review • Quarterly re-scoring mandatory | • Increased retainage (10%+) • Milestone-based payment schedule • Reduced scope; limit new awards • Performance and payment bonds mandatory | Eligible after 12 months with significant documented improvements |
| CRITICAL RISK < 160 pts | DISQUALIFY | • Issue formal rejection letter • Document disqualification basis • Notify VP/Executive and Legal | N/A — Not Applicable | 12-month mandatory waiting period; full re-qualification required |

NOTE: Critical Risk vendors must observe a mandatory 12-month waiting period before re-applying. Re-application requires full re-qualification under the current version of this matrix, submission of documented corrective actions, and VP/Executive approval to enter the evaluation queue.

WWRGD General Contractor Risk Scoring Matrix ¦ Document ID: WWRGD-RSM-GC-001 ¦ Version 2.0 Companion to: WWRGD Enhanced GC RFI (WWRGD_Enhanced_GC_RFI.xlsx) ¦ Effective Date: January 1, 2025